## UAT Test Cases
Test Case ID | User Role | Scenario | Preconditions | Steps | Expected Outcome | Actual Result | Status | Notes
UAT-001 | Staff | Setting up a new shop phone for the first time (pairing) | A new phone/tablet with the browser open to /pair. A 6-digit pairing code has been generated for this outlet. | 1) Open the pairing page on the phone. 2) Type the 6-digit code shown. 3) Tap the 'Pair' button. | The phone pairs successfully, shows a success message with the shop's outlet name/id, then a 4-step checklist of what to do next, and one button to open the listening screen. |  |  | Built and testable today (R-03/P1).
UAT-002 | Staff | Typing a wrong pairing code | On the /pair screen, no code typed yet. | 1) Type a 6-digit code that does not match any active pairing code. 2) Tap 'Pair'. | The phone shows a clear error that the code was refused, keeps the digits on screen so the person can check them, and does not pair. |  |  | Built and testable today.
UAT-003 | Staff | Pairing with no internet connection | Phone's network is disabled or unreachable. | 1) Type a valid 6-digit code. 2) Tap 'Pair' while offline. | The phone shows a network-problem message (different wording from a wrong-code message), keeps the digits, and lets the person try again once back online. |  |  | Built and testable today.
UAT-004 | Staff | Checking at a glance whether the shop phone is listening | The shop phone is paired and sitting in its usual spot, screen on, /capture open. | 1) Glance at the phone from across the counter. | Within about two seconds the person can tell: is it listening right now, and does anything need a tap? One large word plus an icon and colour (never colour alone) says the state. |  |  | Built and testable today.
UAT-005 | Staff | Starting the day (tapping Start/Mulai) inside the allowed window | The phone shows the day hasn't started yet, and the current time is inside the shop's allowed Start window. | 1) Tap the Start button. | The day starts immediately: the phone asks for microphone permission if needed, then shows 'Listening'. A second accidental tap right after does nothing extra (no duplicate day started). |  |  | Built and testable today.
UAT-006 | Staff | Trying to start the day outside the allowed window | The current time is before the shop's opening window or after the Start cut-off for the day. | 1) Look at the Start button. | The Start button is visibly disabled (same size and place, so nothing jumps around) and a short note underneath explains the actual day and time it will work again, written out in full (never 'today'/'tomorrow'). |  |  | Built and testable today.
UAT-007 | Staff | A whole day was never started (nobody tapped Start) | The Start window for a given day has closed and nobody tapped Start that day. | 1) Check the phone the next day. | That day quietly counts as a day off - no alarm, no scary message. This is a known, accepted gap: 'a forgotten Mulai looks like a day off' (see CLAUDE.md known gaps). Flag to Tiffany/Proofed's owner that this can happen if nobody remembers to tap Start. |  |  | Built; known accepted limitation, not a defect - documented in CLAUDE.md Sec 8.
UAT-008 | Staff | Ending the day (tapping End/Selesai) with the two-step confirm | A day is in progress and at least 4 hours have passed since Start. | 1) Tap the End button. 2) On the confirm panel, read the question. 3) Tap 'Not yet, continue'. 4) Tap End again. 5) This time confirm for real. | Tapping 'Not yet, continue' changes nothing and the day keeps running. Confirming for real ends the day, and the debrief (the short Q&A) becomes available right away. |  |  | Built and testable today.
UAT-009 | Staff | Trying to end the day too early (before 4 hours have passed) | A day started less than 4 hours ago. | 1) Look at the main screen. | No End button is shown yet; instead a note says the day can be ended from a specific time, written out in full. |  |  | Built and testable today.
UAT-010 | Staff | The shop phone stops itself automatically if nobody ends the day | A day is left running with nobody tapping End, past the shop's normal closing time. | 1) Leave the phone running past closing time and do nothing. | One hour after the shop's usual closing time, the day ends on its own ('Ended automatically'). The debrief becomes available at that point, same as a manual End. |  |  | Built and testable today (needs a crafted test session, not a real multi-hour wait, for QA; Rangga can observe this on a real day for final confirmation).
UAT-011 | Staff | Cancelling a session by mistake - the safety steps | A day is currently running. | 1) Tap 'Cancel session'. 2) Notice the delete button is greyed out for about a second. 3) Read that today will not be counted if you continue. 4) Either wait 15 seconds without tapping anything, or tap the red delete button once it's enabled. | The delete button cannot be tapped for about the first second (protects against a stray tap). If 15 seconds pass with no tap, the panel closes by itself and nothing is lost. If confirmed, the session is deleted, the phone clearly states today does not count, and the screen becomes a calm 'Cancelled' state (not an alarming one). |  |  | Built and testable today.
UAT-012 | Staff | Reloading the page or losing power mid-day | A day is running; the staff member accidentally reloads the browser tab or the phone restarts. | 1) Reload the page while the day is running. 2) Observe the screen. 3) Tap 'Continue' if shown. | The phone shows an 'Interrupted' state with a Continue button rather than losing the day; tapping Continue resumes the exact same session, not a new one. |  |  | Built and testable today.
UAT-013 | Staff | Opening /capture in a second browser tab or a second device logged in the same way | The shop phone already has /capture open and listening in one tab. | 1) Open /capture in a second tab on the same phone (or a second device with the same pairing). | The second tab clearly shows the phone is busy elsewhere and does not start a second, conflicting recording. |  |  | Built and testable today.
UAT-014 | Staff | Phone loses internet signal mid-day | A day is running and the phone's signal drops briefly. | 1) Turn off Wi-Fi/mobile data for a minute or two while the day is running. 2) Turn it back on. | The main 'Listening' word never changes to an error just because of a signal drop - the phone keeps recording. A small status line below says notes are waiting to be sent, and once signal returns it catches up and says sending succeeded. |  |  | Built and testable today.
UAT-015 | Staff | A note genuinely could not be saved (lost audio) | A rare situation where the phone's queue was full or the server refused a note permanently. | 1) Observe the status line after such an event (can be forced in a test environment, not on a real day). | The phone tells the truth plainly: that particular note is incomplete and cannot be recovered. It does not pretend nothing happened, and it does not blame the staff member. |  |  | Built and testable today in a test environment; naturally occurring on a real day is rare by design.
UAT-016 | Staff | Being asked a handful of quick questions after the day ends (the debrief) | The day has just ended (by End or by the automatic stop) and there is at least one open question for this device. | 1) Notice the debrief card appears on the main screen within a couple of seconds of the day ending. 2) Tap to start. | A card appears quickly inviting the person to answer up to 5 short questions, says roughly how long it will take, and needs no sign-in or password. |  |  | Built and testable today.
UAT-017 | Staff | Answering a debrief question with Yes and a short reason | A debrief question is on screen. | 1) Read the question (a plain-language template, never quoting what anyone said). 2) Tap 'Yes'. 3) Type a short reason. 4) Tap 'Continue'. | Nothing is pre-selected before tapping; the answer and reason are both required before Continue works; once sent, the answer is saved and cannot be edited afterward. |  |  | Built and testable today.
UAT-018 | Staff | Answering a debrief question with No | A debrief question tied to a specific flagged moment is on screen. | 1) Tap 'No'. 2) Type a short reason it didn't happen. 3) Tap 'Continue'. | The question closes as rejected; the flagged moment is marked as not supported by staff and will not be treated as a confirmed fact. No new question appears in its place. |  |  | Built and testable today.
UAT-019 | Staff | Typing a very long reason | A debrief question with the reason box open. | 1) Type well over 500 characters into the reason box. 2) Try to tap 'Continue'. | A live counter shows how many characters have been typed; past the limit, Continue is disabled and a message says how many characters to remove. Nothing is ever silently cut short. |  |  | Built and testable today.
UAT-020 | Staff | Skipping a question instead of answering it | A debrief question is on screen. | 1) Tap 'Skip' without choosing Yes/No or typing anything. | Nothing is sent for that question; it moves to the next one; if reopened later in the same debrief window, it is still blank (nothing half-saved). |  |  | Built and testable today.
UAT-021 | Staff | Running out of time to finish the debrief | A debrief has been open close to its one-hour time limit, with some questions unanswered. | 1) Let the one-hour debrief window run out while a question is still on screen (or before opening it at all). | The debrief screen closes back to the main screen with a plain message: time ran out, any sent answers were kept, anything not yet sent is lost. Unanswered questions are marked as unverified rather than left hanging forever. |  |  | Built and testable today (can be sped up with a crafted test session rather than a real hour's wait).
UAT-022 | Staff | Finishing every question before the hour is up | All of this device's debrief questions have been answered well within the hour. | 1) Answer every open question. 2) Try to start the next day immediately. | Starting the next day is still blocked until the full debrief hour has passed, even though every question was already answered - this is intentional, not a bug. |  |  | Built and testable today. Flag to Rangga/Tiffany that staff may find this counter-intuitive and may want it explained during training.
UAT-023 | Staff | Typing a phone number or someone's name into a debrief reason by mistake | A debrief reason box is open. | 1) Type a reason that includes a phone number and a colleague's name. 2) Submit. | Neither the phone number nor the name is ever shown back to anyone else (supervisor/owner) in the stored record - both are automatically removed before storage. |  |  | Built and testable today at the system level (see the companion SIT workbook for the exact verification steps); from the staff member's point of view, this happens invisibly.
UAT-024 | Staff | Checking what the phone did today without asking anyone | The shop phone has run at least one session today. | 1) Tap the 'History' link at the bottom of the main screen. | A simple time-ordered list shows when Start/End/Cancel happened and whether uploads are going through - with no names, no transcript content, and no device id ever shown. |  |  | Built and testable today.
UAT-025 | Staff | Switching the phone's language between Bahasa Indonesia and English | /capture or any shop-phone screen is open. | 1) Tap the 'ID' or 'EN' control in the top bar. | Every label, button, and message on screen switches to the chosen language immediately, including mid-debrief; numbers, clock times, and anything already typed stay exactly as they are (never machine-translated). |  |  | Built and testable today.
UAT-026 | Staff | A new phone's default language on day one | A freshly paired device that has never had the language changed. | 1) Open /pair or /capture for the first time on a brand-new device. | The screen starts in English by default, regardless of the phone's own system language setting. |  |  | Built and testable today.
UAT-027 | Staff | Reading the privacy notice line on the phone | Any shop-phone screen is open. | 1) Look at the small notice line at the bottom of the screen. | A short, honest line about how the phone handles audio and recording is visible. This line is a notice only - it is not a consent form, and there is no separate 'I agree' screen or button anywhere in the app. |  |  | Built and testable today. NOTE: consent itself is collected outside the app entirely (a paper/email contract with the shop), not inside this product - this is intentional per CLAUDE.md Sec 2 #7b.
UAT-028 | Supervisor | Checking the day's record and the flagged moments that need a decision | A business day has ended and produced at least one proposal-worthy moment. | 1) Open the supervisor view for today. | A day record screen listing today's threads/evidence and the moments that need a supervisor decision. |  |  | NOT YET BUILT - see R-06 (Day record screen). Only a static HTML mockup exists today (docs/design/supervisor-day-record.html); no live screen ships yet.
UAT-029 | Supervisor | Seeing that a staff member answered a debrief question, without knowing who | A debrief question has been answered by a staff member. | 1) Look at the question's status in the supervisor view. | The screen shows 'a staff member answered' - never a name, never a device id, never which specific person. |  |  | Partially built: the underlying rule holds at the API/data level today (can be confirmed by reading the stored answer doc), but no supervisor SCREEN exists yet to see it on - see R-06. NOT YET BUILT as a UI, data-level rule already enforced.
UAT-030 | Supervisor | Reviewing a proposed SOP change before it goes to the owner | A proposal has been generated from gathered evidence. | 1) Open the proposal in the supervisor view. 2) Read the evidence behind it. 3) Approve or reject it for the owner's attention. | The supervisor can see the evidence trail and either pass the proposal forward to the owner or reject it, before anything reaches an approval stage. |  |  | NOT YET BUILT - see R-08 ProposalAgent and R-09 Approval screens. No proposal pipeline exists yet.
UAT-031 | Supervisor | Getting a weekly reminder to review proposals | It is the outlet's configured weekly-review weekday (default Friday) and no review has started in the last 6 local days. | 1) Open the insights/review screen on that day. | A reminder banner appears noting it's time for the weekly review. |  |  | NOT YET BUILT - depends on R-06/insights screen, which has no live UI yet.
UAT-032 | Owner | Approving a supervisor-checked SOP proposal | A proposal has passed supervisor review and is waiting for owner sign-off. | 1) Open the owner approval screen. 2) Review the proposed change and its evidence. 3) Approve it. | Approving the proposal ships it as a new, numbered SOP version; the SOP itself is never edited directly by any other route. |  |  | NOT YET BUILT - see R-09 Approval screens, R-10 SOP versions. No approval screen exists yet. The underlying hard rule ('SOP changes only through proposals', CLAUDE.md Sec 2 #9) is designed but has no shippable UI to click through yet.
UAT-033 | Owner | Viewing the SOP's version history and what changed | At least one SOP version exists beyond the original. | 1) Open the SOP version list. 2) Look at a specific version's before/after. | A simple before/after list shows what changed between SOP versions, in order. |  |  | NOT YET BUILT - see R-10 (before/after diff view was explicitly cut from MVP1 scope, docs/plan.md Sec 10 #51).
UAT-034 | Owner | Reviewing the outcome of a shipped SOP change on its scheduled review date | A SOP version has an outcome review date that has arrived. | 1) Open the review for that SOP version on its scheduled date. 2) Read whether the change worked. | The owner sees a plain assessment of whether the change achieved what was intended, on the date set when it shipped. |  |  | NOT YET BUILT - see R-11 ReviewAgent (Sprint 3, 'close the loop'). No review screen or logic ships yet.
UAT-035 | Judge/Demo visitor | Watching the demo outlet's shop phone pick up a fictional conversation and turn it into a work note | The demo outlet (bee6-playground project) is live; a fictional pre-recorded clip or a live fictional spoken line is available. | 1) Open the demo outlet's /capture page (or watch a prepared recording). 2) Start a day. 3) Speak a fictional work sentence or play a fictional clip. 4) Wait for the status line to show it uploaded. | The judge can see, in real time, the phone listening, a note being captured and uploaded, with nothing alarming and no real shop/person data anywhere on screen. |  |  | Built and testable today (capture + transcribe pipeline). Must use only fictional content - never real Proofed data, per CLAUDE.md Sec 2 #8.
UAT-036 | Judge/Demo visitor | Seeing the full story: evidence becomes a proposal, a supervisor checks it, the owner approves it, it ships | The judge asks to see the whole intended loop, not just capture. | 1) Ask to be walked through evidence -> proposal -> supervisor check -> owner approval -> new SOP version -> scheduled outcome review. | The judge understands the full intended product loop as described in CLAUDE.md Sec 1. |  |  | NOT YET BUILT end-to-end: only the capture + debrief half of the loop is built today (through R-07). The proposal/approval/outcome half (R-08 through R-11) is designed but not shippable yet - be transparent with judges that this is the roadmap, not a live demo, for that portion.
UAT-037 | Judge/Demo visitor | Checking the demo outlet behaves the same as the pilot shop, minus real data | Both the demo project (bee6-playground) and this UAT pass are available. | 1) Run through the staff-role rows above against the demo outlet's live URL instead of a local build. | The demo outlet behaves identically to the rules above, using only fictional demo data, never the Proofed pilot's real data. |  |  | Built and testable today; see the companion SIT workbook's live-demo-URL rows for the technical verification steps.

## Read Me
bee6 — UAT (User Acceptance Testing) Test Cases
Source: docs/tasks/UX-03-journey-design.md (staff phone journey - pairing, Mulai/Selesai/Batalkan, debrief, language toggle), docs/specs/technical-specification.md Sec 8 (session/capture/debrief rules, written here as user-facing behaviour, not code), and CLAUDE.md Sec 1 (the one-paragraph product description, for the proposal/approval/outcome flow).
Lens: plain-language, non-technical scenarios for Rangga, Tiffany, or Proofed's owner to review and sign off on - not technical integration detail (see the companion SIT workbook for that).
Honesty rule followed in this workbook: every row reflects the FULL intended product vision. Rows for features that are designed but not yet built (R-06 supervisor day-record screen, the R-08/R-09/R-10 SOP proposal-approval-versioning pipeline, R-11 outcome review, the full end-to-end judge story) are included, but their Notes column is marked 'NOT YET BUILT' with the relevant R-xx reference. Nothing is claimed ready to test if it is still unbuilt.
What IS built and testable today (per docs/backlog.md as of this workbook's authoring): pairing (/pair), the daily glance and Mulai/Selesai/Batalkan flow (/capture, capture phase P1), upload status and connectivity handling, the tap debrief (R-07), the history log, and the language toggle. P3 (on-device encrypted audio queue) stays OFF on the pilot by design until Rangga's explicit written sign-off (CLAUDE.md Sec 2 #2a) - not included as a testable row here.
Role legend: Staff = shop floor worker on the shared paired phone. Supervisor = checks each proposal before the owner sees it. Owner = approves proposals and reviews outcomes. Judge/Demo visitor = anyone exploring the demo outlet (bee6-playground project) rather than the real Proofed pilot.
Status legend (dropdown in column H): Pass / Fail / Blocked / Not Run.
Data hygiene: every scenario here uses fictional content. Never real Proofed shop/staff/customer data, per CLAUDE.md Sec 2 #8.